## 10-Day Look-Ahead
10-DAY LOOK-AHEAD CONSTRUCTION PROGRAMME
Project: TTP Sullurpet Phase 1 ¦ Client: Vignesh Polymers |  |  |  | Doc No: AZURE-202607-TTP-SDL-001 / Rev 0.1 ¦ Date of Issue: 14-Sep-2026
WORK FRONTS COVERED IN THIS PERIOD
Work Front |  | Nature of Works Covered
Primer Booth |  | Reinforcement fixing, shuttering and concreting works for the raft, wall lifts and tunnel structure at the Primer Booth work front.
Base Coat Booth |  | Reinforcement fixing, shuttering and concreting works for the raft, wall lifts and tunnel structure at the Base Coat Booth work front.
Top Coat Booth |  | Reinforcement fixing, shuttering and concreting works for the raft, wall lifts and tunnel structure at the Top Coat Booth work front, running approximately one cycle behind the Primer and Base Coat Booths.
Hume Pipe |  | Excavation, wet-mix laying, Hume pipe laying and associated chamber civil works along the pipeline alignment.
FOZ 1, 2 & 3 |  | Raft and wall reinforcement, shuttering and concreting works at FOZ 1, 2 & 3.
Sl. No. | Date | Day | Primer Booth | Base Coat Booth | Top Coat Booth | Hume Pipe | FOZ 1, 2 & 3
1 | 15-Sep-2026 | Tuesday | 1. Reinforcement Fixing & Shuttering – Wall, 1st Lift (Ht. 1.2 m) 2. Reinforcement Fixing & Shuttering – Tunnel Raft 3. Concreting – Tunnel Raft 4. Fixing of L-Angle 5. Shuttering – Wall, 3rd Lift | 1. Shuttering – Wall, 1st Lift (Ht. 1.2 m) 2. Concreting – Wall, 1st Lift (Ht. 1.2 m) 3. Reinforcement Fixing & Shuttering – Tunnel Raft 4. Concreting – Tunnel Raft 5. Fixing of L-Angle 6. Shuttering – Wall, 3rd Lift | 1. Reinforcement Fixing & Shuttering – Raft 2. Concreting – Raft 3. Reinforcement Fixing & Shuttering – Tunnel Raft 4. Concreting – Tunnel Raft 5. Fixing of L-Angle 6. Shuttering – Wall, 3rd Lift | 1. Earthwork Excavation 2. Wet-Mix Laying 3. Laying of Hume Pipe (1 m dia.) 4. PCC – Chamber | –
2 | 16-Sep-2026 | Wednesday | 1. Reinforcement Fixing & Shuttering – Wall, 2nd Lift 2. Concreting – Wall, 2nd Lift 3. Concreting – Wall, 3rd Lift 4. Fixing of L-Angle 5. PCC – 2nd Raft 6. Reinforcement Fixing & Shuttering – Tunnel Wall (Ht. 1.2 m) 7. Concreting – Tunnel Wall | 1. Reinforcement Fixing & Shuttering – Wall, 2nd Lift 2. Concreting – Wall, 2nd Lift 3. Concreting – Wall, 3rd Lift 4. Fixing of L-Angle 5. PCC – 2nd Raft 6. Reinforcement Fixing & Shuttering – Tunnel Wall (Ht. 1.2 m) 7. Concreting – Tunnel Wall | 1. Shuttering – Wall, 1st Lift (Ht. 1.2 m) 2. Concreting – Wall, 1st Lift (Ht. 1.2 m) 3. Reinforcement Fixing & Shuttering – Tunnel Raft 4. Concreting – Tunnel Raft 5. Fixing of L-Angle 6. Shuttering – Wall, 3rd Lift | 1. Earthwork Excavation 2. Wet-Mix Laying 3. Laying of Hume Pipe (1 m dia.) 4. PCC – Chamber 5. Reinforcement Fixing – Chamber Raft & Wall | –
3 | 17-Sep-2026 | Thursday | 1. Reinforcement Fixing & Shuttering – 2nd Raft 2. Concreting – 2nd Raft 3. Reinforcement Fixing & Shuttering – Tunnel Roof Slab | 1. Reinforcement Fixing & Shuttering – 2nd Raft 2. Concreting – 2nd Raft 3. Reinforcement Fixing & Shuttering – Tunnel Roof Slab | 1. Reinforcement Fixing & Shuttering – Wall, 2nd Lift 2. Concreting – Wall, 2nd Lift 3. Concreting – Wall, 3rd Lift 4. Fixing of L-Angle 5. PCC – 2nd Raft 6. Reinforcement Fixing & Shuttering – Tunnel Wall (Ht. 1.2 m) 7. Concreting – Tunnel Wall | 1. Earthwork Excavation 2. Wet-Mix Laying 3. Laying of Hume Pipe (1 m dia.) 4. PCC – Chamber 5. Reinforcement Fixing – Chamber Raft & Wall 6. Shuttering – Chamber Wall 7. Concreting – Chamber Raft | 1. Earthwork Excavation 2. PCC – Raft 3. Reinforcement (Rod) Preparation – Raft
4 | 18-Sep-2026 | Friday | 1. Reinforcement Fixing & Shuttering – Wall, 3rd Lift 2. Concreting – Wall, 3rd Lift 3. Fixing of Channel 4. Shuttering & Concreting – Chamber Wall | 1. Reinforcement Fixing & Shuttering – Wall, 3rd Lift 2. Concreting – Wall, 3rd Lift 3. Fixing of Channel 4. Shuttering & Concreting – Chamber Wall | 1. Reinforcement Fixing & Shuttering – 2nd Raft 2. Concreting – 2nd Raft 3. Reinforcement Fixing & Shuttering – Tunnel Roof Slab | 1. Earthwork Excavation 2. Wet-Mix Laying 3. Laying of Hume Pipe (1 m dia.) 4. PCC – Chamber 5. Reinforcement Fixing – Chamber Wall, 1st Lift 6. Shuttering – Chamber Wall 7. Concreting – Chamber Wall | 1. Earthwork Excavation 2. PCC – Raft 3. Reinforcement Fixing & Shuttering – Raft 4. Concreting – Raft
5 | 19-Sep-2026 | Saturday | 1. Waterproofing Works 2. Nozzle Fixing & Grouting 3. Backfilling & Consolidation 4. Shuttering & Concreting – Chamber Wall | 1. Waterproofing Works 2. Nozzle Fixing & Grouting 3. Backfilling & Consolidation 4. Shuttering & Concreting – Chamber Wall | 1. Reinforcement Fixing & Shuttering – Wall, 3rd Lift 2. Concreting – Wall, 3rd Lift 3. Fixing of Channel 4. Shuttering & Concreting – Chamber Wall | 1. Shuttering & Concreting – Chamber Wall, 2nd Lift | 1. Reinforcement Fixing & Shuttering – Wall 2. Concreting – Wall 3. Fixing of L-Angle
6 | 20-Sep-2026 | Sunday | 1. Tile Laying Works 2. Flooring – Wet-Mix Laying, Leveling & Compaction | 1. Tile Laying Works 2. Flooring – Wet-Mix Laying, Leveling & Compaction | 1. Waterproofing Works 2. Nozzle Fixing & Grouting 3. Backfilling & Consolidation 4. Shuttering & Concreting – Chamber Wall | 1. Shuttering & Concreting – Chamber Wall, 3rd Lift | 1. Reinforcement Fixing & Shuttering – Wall 2. Concreting – Wall 3. Fixing of L-Angle
7 | 21-Sep-2026 | Monday | 1. Tile Laying Works 2. Flooring – LDPE Sheet Laying & Reinforcement Mat Fixing | 1. Tile Laying Works 2. Flooring – LDPE Sheet Laying & Reinforcement Mat Fixing | 1. Tile Laying Works 2. Flooring – Wet-Mix Laying, Leveling & Compaction | 1. Shuttering & Concreting – Chamber Wall, 4th Lift | 1. Reinforcement Fixing & Shuttering – Wall 2. Concreting – Wall 3. Fixing of L-Angle
8 | 22-Sep-2026 | Tuesday | 1. Flooring – Reinforcement Mat Fixing 2. VDF (Vacuum De-Watered Flooring) – Concreting | 1. Flooring – Reinforcement Mat Fixing 2. VDF (Vacuum De-Watered Flooring) – Concreting | 1. Tile Laying Works 2. Flooring – LDPE Sheet Laying & Reinforcement Mat Fixing 3. VDF – Concreting | – | –
9 | 23-Sep-2026 | Wednesday | 1. Flooring – Reinforcement Mat Fixing 2. VDF (Vacuum De-Watered Flooring) – Concreting | 1. Flooring – Reinforcement Mat Fixing 2. VDF (Vacuum De-Watered Flooring) – Concreting | 1. Flooring – Reinforcement Mat Fixing 2. VDF (Vacuum De-Watered Flooring) – Concreting | – | –
10 | 24-Sep-2026 | Thursday | – | – | – | – | –
11 | 25-Sep-2026 | Friday | – | – | – | – | –
GENERAL NOTES:
1. PT Line details were yet to be shared by the Client / Engineer-in-Charge and will be incorporated in the next revision of this programme once received.